## OCCASUS ProdPlan-e-view
[35 empty] | Remarks | Location (other than JWC)
Calendaric Timing | [8 empty] | 2019 |  | 2020 | [11 empty] | 2021
[9 empty] | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Exercise Process | Stage 1 | EXSPEC CONFERENCEs | [32 empty] | EXSPEC for STJU21 planned APR 2020, STJU22 anticipated accordingly | bar: 2020 M; 2021 M
|  | CECCs | [32 empty] | EXSPEC for STJU21 planned APR 2020, STJU22 anticipated accordingly | bar: 2020 M; 2021 M
| Stage 2 | IPC | [32 empty] | Anticipated | bar: 2020 J; 2021 S
|  | MPC | [32 empty] | Anticipated | bar: 2020 N; 2021 N
|  | FCC | [32 empty] | Anticipated | bar: 2021 M
|  | EXPLAN final | [32 empty] | Anticipated | bar: 2020 D; 2021 D
| Stage 3 | Phase I A | [32 empty] | Anticipated | bar: 2020 D; 2021 D
|  | Phase I B Academics | [32 empty] | Anticipated | bar: 2020 D; 2021 D
|  | Phase I C KLT | [32 empty] | Anticipated | bar: 2020 D; 2021 D
|  | Phase I D BST | [32 empty] | Anticipated | bar: 2021 A; 2021 A
|  | Phase II A SOPG | [32 empty] | Planned 25 JAN - 12 FEB 21 | bar: 2021 J
|  | Phase II B JOPG | [32 empty] | Anticipated | bar: 2021 F to 2021 M; 2021 A
|  | TA CONOPS | [32 empty] | Anticipated | bar: 2021 F
|  | TA OPLAN | [32 empty] | Anticipated | bar: 2021 F to 2021 M
|  | Phase III A RSOM | [32 empty] | Anticipated | bar: 2021 A; 2021 A
|  | Phase III B Operations | [32 empty] | 24 MAR - 02 APR 20 (TRJU19-2), Planned 25 MAY - 03 JUN & 21 - 30 SEP 21 (STJU21); TRJU19-1 Phase III B (5-14 NOV 2019) is not supported by this contract | bar: 2020 M; 2021 M; 2021 S
|  | Phase IV AAR | [32 empty] | 02 APR for TRJU19-2, Anticipated for STJU21 | bar: 2020 A; 2021 J; 2021 S
| Stage 4 | FIR 1 | [32 empty] | TBD
|  | FIR 2 | [32 empty] | TBD
|  | PXD | [32 empty] | 14 MAY for TRJU19-2 | bar: 2020 M
|  | FER | [32 empty] | 26 JUN for TRJU19-2 | bar: 2020 J
| Supporting Events | MEL / MIL Strat WS | [32 empty] | Anticipated | bar: 2020 D; 2021 D
|  | MEL / MIL IncDev WS | [32 empty] | 13 - 19 JAN for TRJU 19-2, Anticipated for STJU 21 | bar: 2020 J; 2021 M; 2021 A
|  | MEL / MIL Scripting | [32 empty] | 20 - 31 JAN for TRJU 19-2, Anticipated for STJU 21 | bar: 2020 J; 2021 A; 2021 A
|  | Scenario development Kick-Off Meeting | [32 empty] | 01 NOV 19 (TBC) | bar: 2019 N
|  | Force Generation Conference | [32 empty] | Anticipated | bar: 2021 M
|  | Scenario Story Wargame | [32 empty] | Anticipated | bar: 2020 N; 2021 N
|  | OED Workshop | [32 empty] | Anticipated | bar: 2021 M
|  | Network Development Workshop | [32 empty] | Anticipated | bar: 2020 N; 2021 N
|  | INTEL FS WORKSHOP | [32 empty] | Anticipated | MPC location | bar: 2020 N; 2021 N
| SCT | Product | Purpose | SCT Coordination
|  |  |  | 1 | 2 | 3 | 4 | 5
Scenario Production / Product Groups | Strategic Setting and Crisis Conflict Scenario SCT 1 | short-notice liaison (IDMI) | general support | X | Q | Q | Q | Q
|  | additional functional on-site Presence personnel | general support | X | Q | Q | Q | Q | [26 empty] | POLAD role in HICON during Phase II A/B, IIIB, MEL/MIL IncDev and Scripting | bar: 2020 J; 2020 M; 2021 J to 2021 M; 2021 A to 2021 S
|  | additional functional on-site Presence days | general support | X | Q | Q | Q | Q | 2020 J: 20; 2020 M: 15; 2021 J: 10; 2021 F: 20; 2021 M: 20; 2021 A: 10; 2021 M: 20; 2021 A: 15; 2021 S: 20 | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 2, Para 2.1.3. and Chapter 3, Para 3.5.; Total 150 days
|  | Geo Strategic setting | knowledge development | X | S | S | S | S | bar: 2020 F to 2020 M; 2021 F to 2021 M
|  | NIWS | knowledge development | X | S | S | S | S | [26 empty] | Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2020 A; 2020 O; 2021 A; 2021 O
|  | World fact-book incl. supporting documentation | knowledge development | X | S | S | S | S | [26 empty] | CIA world-fact-book model but with Exercise Specific Enhancements. (eg. Link to ORBATs, Research Publications, etc)
|  | Setting Legal Framework /UNSCR | knowledge development | X | S | S | S | S | bar: 2020 S; 2020 N; 2021 S; 2021 N
|  | Biographies - Key Actors | knowledge development | X | S | S | S | S
|  | Status of Forces Agreement/s (SOFA) | strat / oper planning | X | S | S | S | S | [26 empty] | SOFAs as required between potential Host Nations (HN) and NATO | bar: 2020 D; 2021 F; 2021 D
|  | MOU (HNS/INTEL etc) | strat / oper planning | X | S | S | S | S | [26 empty] | Final Coordination between SHAPE (or replicated by JWC) and TA | bar: 2020 D; 2021 F; 2021 D
|  | Military Technical Arrangement | strat / oper planning | X | S | S | S | S | [26 empty] | Final Coordination between SHAPE (or replicated by JWC) and TA | bar: 2020 D; 2021 F; 2021 D
|  | Strategic Correspondence | strat / oper planning | X | S | S | S | S | [26 empty] | NATO HQ/NAC/SHAPE correspondence with TA (primarily letters)
|  | Road to STARTEX Event Database | strat / oper execution | X | S | S | S | S | bar: 2020 S; 2021 A; 2021 S
|  | Supplementary Documentation | multi | S | S | S | X | S | [26 empty] | These can consist of fictional "Think Tank" Publications / Research Papers / JOKER articles as required to supplement existing information or fill in gaps. First Products (if required) are published with Fact Books.
|  | Coordination of BLUE book repository data conversion for planning | strat / oper planning | S | X | Q | Q | S | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.2, 3.3.3.5., 3.4.9.2. and 3.4.9.5.; The data is provided in TOPFAS (OMT, eFGMT) format, or as per Direction and Guidance from Chief Scenario. | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | Input to Crisis Response Information Package (CRIP) | strat / oper planning | S | S | X | S | S | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to Crisis Situation Updates (CSU) 1 ,2 | strat / oper planning | S | S | X | S | S | [26 empty] | Final Number and Dates TBD. | bar: 2020 D to 2021 J; 2021 D
|  | Input to Crisis Situation Updates (CSU) 3 - N | knowledge development | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2021 F to 2021 A
|  | Road to Crisis (RTC) | strat / oper planning | X | S | S | S | S | bar: 2020 S; 2021 S
|  | Help for Dates | knowledge development | X | S | S | S | S | [26 empty] | Tool to clearly link Exercise Dates to Real World Dates and manage Time Jumps or Time Compressions as required. (Examples Available at JWC) | bar: 2020 M; 2020 J; 2021 M; 2021 J
|  | Input to Network/s Database | strat / oper planning | S | S | X | S | S | [26 empty] | To include indicators and warnings | bar: 2020 M; 2020 J; 2021 M; 2021 J
|  | Input to Scenario Wargaming | ex design coord | S | S | S | S | S | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to OED Workshop | ex design coord | S | S | S | S | Q | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2021 F to 2021 M
|  | RFI Subfunction / Support (BLUE / GREEN) | knowledge development | X | S | S | S | S | [26 empty] | Support also the ongoing RFI activities for TRJU 19-2, RFI Process starts with release of CRIP and runs through ENDEX. Using TOPFAS for Blue/Green RFIs and INTEL FS for Red RFIs.
| Comprehensive Operational Planning SCT 2 | short-notice liaison (IDMI) | general support | Q | X | Q | Q | Q
|  | additional functional on-site Presence personnel | general support | Q | X | Q | Q | Q | 2020 J: 1; 2020 M: 2; 2021 J: 2; 2021 F: 2; 2021 M: 1; 2021 A: 1; 2021 M: 2; 2021 A: 2; 2021 S: 2 | MIL-POL & MIL-STRAT roles in HICON during Phase II A/B, IIIB, MEL/MIL IncDev and Scripting
|  | additional functional on-site Presence days, per person | general support | Q | X | Q | Q | Q | 2020 J: 20; 2020 M: 15; 2021 J: 10; 2021 F: 20; 2021 M: 20; 2021 A: 10; 2021 M: 20; 2021 A: 15; 2021 S: 20 | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 2, Para 2.1.3. and Chapter 3, Para 3.5.; Total 150 days for primary SCT SME, 100 days for add. SME
|  | Tasker for Strategic Military Assessment (SMA) | strat / oper planning | S | X | S | S | S | [26 empty] | Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | Tasker for MRO | strat / oper planning | S | X | S | S | S | [26 empty] | Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | BLUE Force Pool | strat / oper planning | S | X | S | S | S | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.4.9.2. | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | Coordination of BLUE book repository data conversion for planning | strat / oper planning | S | X | Q | Q | S | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.2, 3.3.3.5., 3.4.9.2. and 3.4.9.5.; The data is provided in TOPFAS (OMT, eFGMT) format, or as per Direction and Guidance from Chief Scenario. | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | Stratcom Framework | strat / oper planning | S | X | S | S | S | [26 empty] | Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | CONOPS Approval Letter / FAD | strat / oper planning | S | X | S | S | S | [26 empty] | Begin work immeadiately upon receipt of TA CONOPS in coordination with JWC Assessment Team SMEs | bar: 2021 M; 2021 O
|  | NID | strat / oper planning | S | X | S | S | S | [26 empty] | Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2021 J; 2021 S
|  | CRM Approval | strat / oper planning | S | X | S | S | S | [26 empty] | Linked with OPLAN approval, but TA may request CRMs earlier | bar: 2021 F
|  | OPLAN / ROEREQ / TCSOR Approval Letter - Input | strat / oper planning | S | X | S | S | S | [26 empty] | Begin work immeadiately upon receipt of TA OPLAN in coordination with JWC Assessment Team SMEs | bar: 2021 F
|  | JPDAL Approval (Included in CONOPS / OPLAN approval) | strat / oper planning | S | X | S | S | S | [26 empty] | Begin work immeadiately upon receipt of TA OPLAN in coordination with JWC Assessment Team SMEs | bar: 2021 F
|  | HVAL Approval (Included in CONOPS / OPLAN approval) | strat / oper planning | S | X | S | S | S | [26 empty] | Begin work immeadiately upon receipt of TA OPLAN in coordination with JWC Assessment Team SMEs | bar: 2021 F
|  | Allied Dispostion List (ADL) Approval | strat / oper planning | S | X | S | S | S | [26 empty] | Begin work immeadiately upon receipt of TA ADL in coordination with JWC Force Gen SME and JWC Assessment Team SMEs | bar: 2021 F
|  | Allied Force List (AFL) | strat / oper planning | S | X | S | S | S | [26 empty] | Begin work immeadiately upon receipt of TA ADL in coordination with JWC Force Gen SME and JWC Assessment Team SMEs | bar: 2021 F
|  | NED | strat / oper planning | S | X | S | S | S | [26 empty] | Subject to ACTPRED. Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2021 A to 2021 M
|  | ACTORD | strat / oper planning | S | X | S | S | S | [26 empty] | Subject to ACTPRED. Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2021 A to 2021 M
|  | ROEIMPL | strat / oper planning | S | X | S | S | S | [26 empty] | Subject to ACTPRED. Ref: Allied Command Operations Planning Directive (COPD) V2.0 4 October 2013 | bar: 2021 A to 2021 M
|  | Supplementary Documentation | multi | S | S | S | X | S | [26 empty] | These can consist of fictional "Think Tank" Publications / Research Papers / JOKER articles as required to supplement existing information or fill in gaps. First Products (if required) are published with Fact Books.
|  | Input to Crisis Response Information Package (CRIP) | strat / oper planning | S | S | X | S | S | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to Crisis Situation Updates (CSU) 1 ,2 | strat / oper planning | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2020 D to 2021 J; 2021 D
|  | Input to Crisis Situation Updates (CSU) 3 - N | knowledge development | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2021 F to 2021 A
|  | Input to Scenario Wargaming | ex design coord | S | S | S | S | S | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to OED Workshop | ex design coord | S | S | S | S | Q | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2021 F to 2021 M
|  | RFI Subfunction / Support (BLUE / GREEN) | knowledge development | X | S | S | S | S | [26 empty] | Support also the ongoing RFI activities for TRJU 19-2, RFI Process starts with release of CRIP and runs through ENDEX. Using TOPFAS for Blue/Green RFIs and INTEL FS for Red RFIs.
| Military Joint Intelligence SCT 3 | short-notice liaison (IDMI) | general support | Q | Q | X | Q | Q
|  | additional functional on-site Presence personnel | general support | Q | Q | X | Q | Q | 2020 J: 1; 2020 M: 2; 2021 M: 1; 2021 A: 1; 2021 M: 2; 2021 A: 1; 2021 S: 2 | JISR / NIFC roles in EXCON during Phase II A/B, IIIB, MEL/MIL IncDev and Scripting
|  | additional functional on-site Presence days, per person | general support | Q | Q | X | Q | Q | 2020 J: 20; 2020 M: 15; 2021 M: 10; 2021 A: 10; 2021 M: 20; 2021 A: 15; 2021 S: 20 | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 2, Para 2.1.3. and Chapter 3, Para 3.5.; Total 110 days for primary SCT SME, 55 days for add. SME
|  | Enemy Military ORBATs Database (Intel FS) | strat / oper planning | S | S | X | S | S | [26 empty] | To include BSO import file development (EXCEL Spreadsheet) | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Network/s Database | strat / oper planning | S | S | X | S | S | [26 empty] | To include indicators and warnings | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Supplementary Documentation | multi | S | S | S | X | S | [26 empty] | These can consist of fictional "Think Tank" Publications / Research Papers / JOKER articles as required to supplement existing information or fill in gaps. First Products (if required) are published with Fact Books.
|  | Crises Response Information Package (CRIP) | strat / oper planning | S | S | X | S | S | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Crises Situation Updates (CSU) 1 ,2 | strat / oper planning | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2020 D to 2021 J; 2021 D
|  | Crises Situation Updates (CSU) 3 - N | knowledge development | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2021 F to 2021 A
|  | STARTEX Package | strat / oper execution | S | S | X | S | S | [26 empty] | Developed after MEL/MIL Scripting; Final content as per Direction and Guidance by Chief Scenario | bar: 2021 M to 2021 A
|  | SUPINTREP/INTSUM | knowledge development | S | S | X | S | S | [26 empty] | Number and Dates TBD
|  | DIU | knowledge development | S | S | X | S | S | [26 empty] | During Phase III B, No Drafts. Dynamically scripted | bar: 2020 M; 2021 M; 2021 S
|  | Input to Scenario Wargaming | ex design coord | S | S | S | S | S | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to OED Workshop | ex design coord | S | S | S | S | Q | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2021 F to 2021 M
|  | RFI Subfunction / Support (RED) | knowledge development | S | S | X | S | S | [26 empty] | Support also the ongoing RFI activities for TRJU 19-2, RFI Process starts with release of CRIP and runs through ENDEX. Using TOPFAS for Blue/Green RFIs and INTEL FS for Red RFIs.
| Military Joint Tragetting SCT 4 | short-notice liaison (IDMI) | general support | Q | Q | Q | X | Q
|  | additional functional on-site Presence personnel | general support | Q | Q | Q | X | Q | 2020 J: 1; 2020 M: 2; 2021 M: 1; 2021 A: 1; 2021 M: 2; 2021 A: 1; 2021 S: 2 | Deliberate Targeting SME / JTST Coordinator roles in EXCON during Phase II A/B, IIIB, MEL/MIL IncDev and Scripting
|  | additional functional on-site Presence days, per person | general support | Q | Q | Q | X | Q | 2020 J: 20; 2020 M: 15; 2021 M: 10; 2021 A: 10; 2021 M: 20; 2021 A: 15; 2021 S: 20 | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 2, Para 2.1.3. and Chapter 3, Para 3.5.; Total 110 days for primary SCT SME, 55 days for add. SME
|  | JTLS Target and DPI Import File | strat / oper planning & execution | S | S | S | X | S | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Support to INTEL FS BSO Place Import File | strat / oper planning | S | S | S | X | S | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Geo Mil Objects Layer | strat / oper planning | S | S | S | X | S | bar: 2020 J; 2020 A; 2021 J; 2021 A
|  | SACEUR Tgt Board Presentations | strat / oper execution | S | S | S | X | S | bar: 2020 D to 2021 J; 2021 A to 2021 M; 2021 A to 2021 S; 2021 D
|  | SACEUR Tgt Dir and Tgt Set Approval | strat / oper execution | S | S | S | X | S | bar: 2020 D to 2021 J; 2021 A to 2021 M; 2021 A to 2021 S; 2021 D
|  | JTS Data Set | strat / oper planning & execution | S | S | S | X | S | [26 empty] | A JTS Data Set comprises 26 fields of data for every target entity. Data Sets are developed from JWC-provided data sources (e.g. Geo, Scenario, Real-World). | bar: 2020 J; 2020 A; 2021 J; 2021 A
|  | Basic Tgt Graphics | strat / oper planning & execution | S | S | S | X | S | bar: 2020 J; 2020 A; 2021 J; 2021 A
|  | Support to Intermediate Electronic Tgt Folder development | strat / oper planning & execution | S | S | S | X | S
|  | Support to Advanced Electronic Tgt Folder development | strat / oper planning & execution | S | S | S | X | S
|  | Target Intel and BDA Reporting | strat / oper planning & execution | S | S | S | X | S | bar: 2020 M; 2021 M; 2021 S
|  | Supplementary Documentation | multi | S | S | S | X | S | [26 empty] | These can consist of fictional "Think Tank" Publications / Research Papers / JOKER articles as required to supplement existing information or fill in gaps. First Products (if required) are published with Fact Books.
|  | Input to Crisis Response Information Package (CRIP) | strat / oper planning | S | S | X | S | S | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to Crisis Situation Updates (CSU) 1 ,2 | strat / oper planning | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2020 D to 2021 J; 2021 D
|  | Input to Crisis Situation Updates (CSU) 3 - N | knowledge development | S | S | X | S | S | [26 empty] | Final Number and Dates TBD | bar: 2021 F to 2021 A
|  | Input to Network/s Database | strat / oper planning | S | S | X | S | S | [26 empty] | To include indicators and warnings | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to Scenario Wargaming | ex design coord | S | S | S | S | S | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2020 O to 2020 N; 2021 O to 2021 N
|  | Input to OED Workshop | ex design coord | S | S | S | S | Q | [26 empty] | Subject to framework laid out in the Scenario Storybook and Direction and Guidance from Chief Scenario. | bar: 2021 F to 2021 M
|  | RFI Subfunction / Support (BLUE / RED) | knowledge development | S | S | X | S | S | [26 empty] | Support also the ongoing RFI activities for TRJU 19-2, RFI Process starts with release of CRIP and runs through ENDEX. Using TOPFAS for Blue/Green RFIs and INTEL FS for Red RFIs.
| Information and Knowledge Management SCT 5 | short-notice liaison (IDMI) | general support | Q | Q | Q | Q | X
|  | TOPFAS SAT ES | multi | S | S | S | S | X | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.5. and Para 3.4.9.5. | bar: 2020 O; 2021 O
|  | TOPFAS OPT (TA/JWC) | multi | S | S | S | S | X | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.5. and Para 3.4.9.5. | bar: 2020 N; 2021 N
|  | Coordination of BLUE book repository data conversion for planning | strat / oper planning | S | X | Q | Q | S | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.2, 3.3.3.5., 3.4.9.2. and 3.4.9.5.; The data is provided in TOPFAS (OMT, eFGMT) format, or as per Direction and Guidance from Chief Scenario. | bar: 2020 N to 2020 D; 2021 N to 2021 D
|  | LOGFAS | multi | S | S | S | S | X | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.5. and Para 3.4.9.5. | bar: 2020 N; 2021 N
|  | INTELFS | multi | S | S | S | S | X | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.3.3.5. and Para 3.4.9.5. | bar: 2020 O; 2021 O
|  | RFI database & function / management | knowledge development | S | S | S | S | X | [26 empty] | Support also the ongoing RFI activities for TRJU 19-2, RFI Process starts with release of CRIP and runs through ENDEX. Using TOPFAS for Blue/Green RFIs and INTEL FS for Red RFIs.
|  | Scenario Web | multi | S | S | S | S | X | [26 empty] | Ref. IFIB ACT-JWC -19-09, Part III Section B Chapter 3, Para 3.4.9.5.; The Scenario Web requires maintenance from release of the Geo Strategic setting | bar: 2020 F to 2020 M; 2021 F to 2021 M
|  | Post Exercise Setting and Scenario Archive | multi | S | S | S | S | X
[9 empty] | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
[9 empty] | 2019 |  | 2020 | [11 empty] | 2021
|  |  |  | X = supported SCT |  |  |  |  | J: Exercise Event TRJU 19; D: Exercise Event STJU 21; D: Exercise Event STJU 21 | Exercise Event STJU 22
S = supporting SCT
|  |  |  | Q = no role |  |  |  |  | J: Production / Maintenance Phase; O: D; D: Delivery of Initial Draft; S: X; D: Delivery of Initial Draft | Delivery of final product
[9 empty] | J: Product delivered on time / no issues; O: -; D: Product delayed / minor issues; D: Product delayed / minor issues | Product not delivered / major issues